## Tasks
Date 10/03/2026 | Task | Potential Marks | Task Start Date | Actual Start Date | Task Completion Date | Expected Completion Date
2026-03-10 | Description of Task
Date 10/03/2026 | Description of Task | 10% | Task Start Date | Actual Start Date | Task Completion Date | Expected Completion Date
| Business context -purpose, target users, and outcomes. | 10 | 2026-03-15 | 2026-03-15 | 2026-03-31 | COMPLETED
| Identify stakeholders |  | 2026-03-15 | 2026-03-15 | 2026-03-21 | COMPLETED
| User requirements - user stories |  | 2026-03-15 | 2026-03-15 | 2026-03-19 | COMPLETED
| Value proposition - benefits |  | 2026-03-15 | 2026-03-15 | 2026-03-21 | COMPLETED
| Design User Flow |  | 2026-03-15 | 2026-03-15 | 2026-03-30 | COMPLETED
| DESIGN | 45%
Database
| Schema - Tables, relationships, constraints |  | 2026-03-17 | 2026-03-17 | 2026-03-18 | COMPLETED
| CRUD operations - Create, Read, Update, Delete functionality |  | 2026-03-18 | 2026-03-18 | 2026-03-18 | COMPLETED
Login / Registration
| Design user-friendly forms - Include fields, placeholders, buttons |  | 2026-03-19 | 2026-03-21 | 2026-03-28 | COMPLETED
| Design – Dashboard |  | 2026-03-20 |  |  | OUT OF SCOPE
| Create dashboard wireframes - Mockups for UI review |  | 2026-03-20 | 2026-03-20 | 2026-03-20 | COMPLETED
| Design – Landing Page / Chat Forum |  | 2026-03-19 | 2026-03-19 | 2026-03-28 | COMPLETED
| Define page layout and branding - Colors, fonts, logo, style guide |  | 2026-03-19 | 2026-03-19 | 2026-03-21 | COMPLETED
| Design navigation structure - Links to dashboard, login, etc. |  | 2026-03-21 | 2026-03-20 | 2026-03-29 | COMPLETED
| Create wireframes / mockups - Use Figma or pen sketches |  | 2026-03-19 | 2026-03-19 | 2026-03-30 | COMPLETED
| GIT & README | 10
| Create a repository for Capstone Project |  | 2026-03-15 | 2026-03-15 | 2026-03-15 | COMPLETED
| README - instructions |  | 2026-03-15 | 2026-03-15 | 2026-03-30 | COMPLETED
| Branch Structure Setup |  | 2026-03-15 | 2026-03-15 | 2026-03-15 | COMPLETED
| Documentation | 15
| Problem, stakeholders, and solution |  | 2026-03-14 | 2026-03-14 | 2026-03-19 | COMPLETED
| Architecture - MVC, DB, UI |  | 2026-03-19 | 2026-03-19 | 2026-03-30 | COMPLETED
| Comment code properly - Functions, classes, important logic |  | 2026-03-19 | 2026-03-20 | 2026-03-31 | COMPLETED
| Organize documentation logically - README, code comments, diagrams |  | 2026-03-21 | 2026-03-21 | 2026-03-31 | COMPLETED
| Planning | 10
| Milestones/sprints - Helps track progress and effort |  | 2026-03-10 | 2026-03-10 | 2026-03-12 | COMPLETED
| Effort estimation |  | 2026-03-11 | 2026-03-11 | 2026-03-12 | COMPLETED
| Progress tracking |  | 2026-03-10 | 2026-03-11 | 2026-03-31 | COMPLETED
| Plan next steps - Prioritize unfinished tasks |  | 2026-03-22 | 2026-03-22 | 2026-03-31 | COMPLETED
| Testing | 10
| Landing Page |  | 2026-03-26 | 2026-03-26 | 2026-03-28 | COMPLETED
| Dashboard |  |  |  |  | OUT OF SCOPE
| Chat forum |  | 2026-03-20 | 2026-03-20 | 2026-03-26 | COMPLETED
| login/registration |  | 2026-03-25 | 2026-03-25 | 2026-03-27 | COMPLETED
| API functionality |  | 2026-03-26 | 2026-03-26 | 2026-03-30 | COMPLETED
| UI responsiveness |  | 2026-03-25 | 2026-03-25 | 2026-03-30 | COMPLETED
| Delivery | 45%
| Quality of Server | 10
| MVC Structure |  | 2026-03-18 | 2026-03-18 | 2026-03-30 | COMPLETED
| Code Structure |  | 2026-03-19 | 2026-03-19 | 2026-03-30 | COMPLETED
| Code Quality & Readability |  | 2026-03-19 | 2026-03-19 | 2026-03-30 | COMPLETED
| User Interface | 10
| Responsive Layout |  | 2026-03-19 | 2026-03-19 | 2026-03-28 | COMPLETED
| Functionality | 10
| Confirm all functions work as intended - Login, CRUD |  | 2026-03-25 | 2026-03-25 | 2026-03-30 | COMPLETED
| Database | 5
| Test CRUD operations - Check efficiency and accuracy |  | 2026-03-18 | 2026-03-18 | 2026-03-18 | COMPLETED
Prepare PowerPoint Presentation | Live Demo - stick to timeframe (10-15mins)
| Prepare demo script - Highlight features and workflows | 10 | 2026-03-28 | 2026-03-28 | 2026-03-30 | 2026-03-30
| Rehearse clear and concise delivery -Practice timing and tone |  | 2026-03-29 | 2026-03-29 | 2026-04-01 | 2026-04-01
| Prepare for stakeholder questions - FAQs and edge cases |  | 2026-03-30 | 2026-03-30 | 2026-03-30 | 2026-03-30
| Ensure live demo works reliably - Test environment setup |  | 2026-03-31 | 2026-03-31 | 2026-03-30 | 2026-03-30
| Troubleshooting |  | 2026-04-01 | 2026-04-01 | 2026-04-01 | 2026-04-01